## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
Project Timeline
CSE 6242 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Team 179 | Elise Reppond, Alex Johnson, Tad Kabage, Shloka Parvatrao, and Joanna Rashid
Project start date: | 2023-03-01 |  |  |  |  | March | [34 empty] | April
Scrolling increment: | 0 | time axis 2023-03-01 to 2023-04-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-01 to 2023-04-25
Proposal
Presentation Slides | On Track | Tad | 75% | 2023-03-01 | 4
Sources and citations | On Track | Joanna | 75% | 2023-03-01 | 4
Gantt Chart | On Track | Elise | 100% | 2023-03-01 | 4
Write-up | On Track | Shloka | 75% | 2023-03-01 | 4
Video | On Track | Alex | 75% | 2023-03-01 | 4
Development
Data sources finalized | On Track |  | 50% | 2023-03-07 | 7
Objectives finalized | On Track |  | 50% | 2023-03-07 | 10
Clean datasets and combine | On Track |  | 0% | 2023-03-10 | 11
Create filtering |  |  | 0% | 2023-03-12 | 10
Integrate prediction |  |  | 0% | 2023-03-12 | 24
Generate visuals/tables |  |  | 0% | 2023-03-16 | 20
App development |  |  | 0% | 2023-03-19 | 30
Deadlines
Progress Report | Milestone |  | 0% | 2023-03-25 | 6 | bar: 2023-03-25 to 2023-03-30
Final Report | Milestone |  | 0% | 2023-04-10 | 15 | bar: 2023-04-10 to 2023-04-24
Final Presentation | Milestone |  | 0% | 2023-04-10 | 15 | bar: 2023-04-10 to 2023-04-24

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2023-03-01 |  |  |  |  | March | [27 empty] | April
Scrolling increment: | 5 | time axis 2023-03-06 to 2023-04-30
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TITLE 1
Task 1 | Goal | Name | 25% | 2023-03-01 | 3
Task 2 | Milestone |  |  | 2023-03-06 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2023-02-26 | 10
Task 4 | Milestone |  |  | 2023-03-21 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2023-03-07 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-03-07 | 13
Task 2 | On Track |  | 50% | 2023-03-09 | 9
Task 3 | Low Risk |  | 33% | 2023-03-14 | 11
Task 4 | Milestone |  |  | 2023-03-16 | 1 | bar: T
Task 5 |  |  |  | 2023-03-17 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-03-16 | 4
Task 2 | Med Risk |  |  | 2023-03-19 | 14
Task 3 | On Track |  |  | 2023-04-03 | 6
Task 4 | Goal |  |  | 2023-04-07 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2023-03-07 | 19
TITLE 4
Task 1 |  |  |  | 2023-04-10 | 15
Task 2 |  |  |  | 2023-04-24 | 5
Task 3 | Milestone |  |  | 2023-06-05 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2023-03-01 |  |  |  |  | March | [27 empty] | April
Scrolling increment: | 5 | time axis 2023-03-06 to 2023-04-30
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-06 to 2023-04-30
TITLE 1
Task 1 | Goal | Name | 25% | 2023-03-01 | 3
Task 2 | Milestone |  |  | 2023-03-06 | 1 | bar: 2023-03-06
Task 3 | Low Risk |  | 50% | 2023-02-26 | 10
Task 4 | Milestone |  |  | 2023-03-21 | 1 | bar: 2023-03-21
Task 5 | Med Risk |  | 10% | 2023-03-07 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-03-07 | 13
Task 2 | On Track |  | 50% | 2023-03-09 | 9
Task 3 | Low Risk |  | 33% | 2023-03-14 | 11
Task 4 | Milestone |  |  | 2023-03-16 | 1 | bar: 2023-03-16
Task 5 |  |  |  | 2023-03-17 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-03-16 | 4
Task 2 | Med Risk |  |  | 2023-03-19 | 14
Task 3 | On Track |  |  | 2023-04-03 | 6
Task 4 | Goal |  |  | 2023-04-07 | 3 | 2023-04-07: 2; 2023-04-08: 2; 2023-04-09: 2
Task 5 | Low Risk |  |  | 2023-03-07 | 19
TITLE 4
Task 1 |  |  |  | 2023-04-10 | 15
Task 2 |  |  |  | 2023-04-24 | 5
Task 3 | Milestone |  |  | 2023-06-05 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one